EXECUTIVE RESOURCE

# Year-End Fundraising
Planning Calendar

September 2026 - January 2027

A relationship-centered roadmap for planning, stewardship, Giving Tuesday, year-end communications, donor appreciation, and post-campaign follow-up.

Planning principle The strongest year-end campaigns do not begin in November. They begin with relationships built throughout the year.

Prepared by Donor Outreach by JMA

Changing Conversations into Commitments  |  616-453-8711

START HERE

# How to Use This Planning Calendar

Use this resource during weekly fundraising and leadership meetings from September through January.

| Step | Leadership action | What good execution looks like |
| --- | --- | --- |
| 1 | Name one campaign owner | Give one person responsibility for maintaining the calendar, collecting updates, and escalating missed deadlines. |
| 2 | Confirm dates and audiences | Adapt the suggested cadence to your organization, donor segments, channels, and approval process. |
| 3 | Assign every action | Enter an owner and due date for each task. A plan without ownership is only a list of intentions. |
| 4 | Review weekly | Use the status columns to identify decisions, risks, delays, and donor groups needing personal outreach. |
| 5 | Record what worked | Capture results and lessons in January so next year's campaign begins with evidence, not assumptions. |

## Campaign Leadership Snapshot

| Decision | Organization entry |
| --- | --- |
| Campaign goal | ____________________________________________ |
| Campaign owner | ____________________________________________ |
| Executive sponsor | ____________________________________________ |
| Board liaison | ____________________________________________ |
| Primary donor audiences | ____________________________________________ |
| Core impact message | ____________________________________________ |
| Final gift-processing date | ____________________________________________ |

2026 anchor date Giving Tuesday is Tuesday, December 1, 2026. Build toward it as a campaign milestone, not a one-day event.

AT A GLANCE

# Master Campaign Milestones

Confirm these dates first, then adjust the detailed schedules that follow.

| Timing | Phase | Primary outcome |
| --- | --- | --- |
| September 1-11 | Strategy | Confirm goal, audiences, case for support, budget, channels, and owners. |
| September 14-30 | Readiness | Clean data, segment donors, gather stories, draft creative, and begin personal stewardship. |
| October 1-30 | Stewardship | Thank donors, report impact, re-engage lapsed supporters, and prepare campaign assets. |
| November 2-13 | Early momentum | Finalize testing, approvals, landing pages, phone lists, and board activation. |
| November 16-30 | Countdown | Begin public buildup, personal outreach, reminders, and match/challenge messaging. |
| December 1 | Giving Tuesday | Coordinate email, social, telephone outreach, gift processing, and rapid thanks. |
| December 2-18 | Year-end case | Share progress, stories, impact, and a clear December 31 opportunity. |
| December 21-31 | Final stretch | Increase urgency without losing gratitude; closely monitor responses and processing. |
| January 4-29 | Follow-up | Thank, fulfill, reconcile, report, survey, and document lessons. |

## Weekly Leadership Review

| Lens | Question |
| --- | --- |
| Progress | Are we on track against revenue, participation, retention, and response goals? |
| Relationships | Which donor groups need appreciation or a personal conversation this week? |
| Readiness | What content, data, technology, or approvals could delay the next communication? |
| Coordination | Do staff, board members, volunteers, and outside partners know their next action? |
| Learning | What are donors telling us, and what should we adjust now? |

SEPTEMBER PLANNING CHECKLIST

# Build the Foundation Before the Ask

September objective: align leadership, clarify the case for support, prepare donor data, and begin reconnecting personally.

| Done | Timing | Action | Owner | Due |
| --- | --- | --- | --- | --- |
| ☐ | Sept. 1-4 | Confirm fundraising goal, expense budget, net revenue target, and success measures. | _____ | _____ |
| ☐ | Sept. 1-4 | Appoint campaign owner and clarify staff, executive, board, and vendor responsibilities. | _____ | _____ |
| ☐ | Sept. 7-11 | Define the need, donor-facing outcome, campaign theme, and one clear call to action. | _____ | _____ |
| ☐ | Sept. 7-11 | Select donor segments: current, LYBUNT, SYBUNT, monthly, major, new, and inactive. | _____ | _____ |
| ☐ | Sept. 7-11 | Audit addresses, email addresses, phone numbers, consent/preferences, and suppressions. | _____ | _____ |
| ☐ | Sept. 14-18 | Review prior-year response, average gift, channel results, retention, and timing. | _____ | _____ |
| ☐ | Sept. 14-18 | Identify 3-5 specific impact stories, outcomes, photos, and donor proof points. | _____ | _____ |
| ☐ | Sept. 14-18 | Map direct mail, email, social, phone, text, website, and acknowledgment touchpoints. | _____ | _____ |
| ☐ | Sept. 21-25 | Create first drafts of the appeal, emails, scripts, landing page, and gift form. | _____ | _____ |
| ☐ | Sept. 21-25 | Secure match/challenge details and confirm language, limits, and deadlines. | _____ | _____ |
| ☐ | Sept. 21-30 | Begin stewardship calls to priority donors and record interests or concerns. | _____ | _____ |
| ☐ | Sept. 28-30 | Hold readiness review; approve October stewardship and November launch dates. | _____ | _____ |

September leadership checkpoint Can every team member explain why this campaign matters, who should hear from us, and what action we want the donor to take?

OCTOBER STEWARDSHIP SCHEDULE

# Earn Attention Through Appreciation

October objective: demonstrate impact, listen to donors, and prepare the relationship before fundraising intensity increases.

| Timing | Touchpoint | Action / message goal | Owner |
| --- | --- | --- | --- |
| Oct. 1-2 | Leadership alignment | Confirm stewardship audiences and outreach assignments; brief staff and board ambassadors. | _____ |
| Oct. 5-9 | Thank-you outreach | Call recent, recurring, upgraded, major, and long-term donors with no ask. | _____ |
| Oct. 12-16 | Impact update | Send a concise story showing what donor generosity made possible. | _____ |
| Oct. 12-16 | Listening | Ask a small donor group what motivates them, what they value, and how they prefer updates. | _____ |
| Oct. 19-23 | Lapsed re-engagement | Reach LYBUNT/SYBUNT donors with appreciation, a brief update, and an invitation to reconnect. | _____ |
| Oct. 19-23 | Board activation | Give each board member a manageable list for calls, notes, introductions, or social sharing. | _____ |
| Oct. 26-30 | Campaign preview | Tell priority donors what the organization hopes to accomplish before year-end. | _____ |
| Oct. 26-30 | Readiness review | Finalize data, creative, gift processing, response handling, and Giving Tuesday calendar. | _____ |

## Stewardship Conversation Guide

| Moment | Suggested approach |
| --- | --- |
| Open | Thank you for the difference your support has made. |
| Impact | Share one brief, specific outcome—not a list of organizational activities. |
| Listen | Ask what part of the mission matters most and whether the donor has questions. |
| Confirm | Verify preferences and contact information naturally, with permission. |
| Close | Thank the donor again. Do not turn an appreciation call into an unexpected solicitation. |
| Record | Capture interests, concerns, preferences, commitments, and needed follow-up. |

Measure more than gifts Track conversations completed, preferences learned, information corrected, follow-ups requested, and donor sentiment.

GIVING TUESDAY PREPARATION TIMELINE

# Turn One Day Into a Five-Week Campaign

Giving Tuesday: Tuesday, December 1, 2026. Use the weeks before and after it to build connection and momentum.

| Timing | Phase | Critical actions | Owner |
| --- | --- | --- | --- |
| Nov. 2-6 | 4 weeks out | Finalize goal, theme, audiences, match, landing page, gift form, tracking links, scripts, and approval route. | _____ |
| Nov. 9-13 | 3 weeks out | Brief staff and board; prepare ambassadors; test all links, receipts, forms, and mobile experience. | _____ |
| Nov. 16-20 | 2 weeks out | Share the need and impact story; begin priority donor calls; introduce match or challenge. | _____ |
| Nov. 23-25 | 1 week out | Send campaign preview; schedule emails/social; confirm phone lists and rapid-response responsibilities. | _____ |
| Nov. 26-29 | Holiday window | Lead with gratitude. Use restrained reminders and avoid crowding Thanksgiving communications. | _____ |
| Nov. 30 | Day before | Send a concise preview; complete final systems check; confirm coverage and escalation plan. | _____ |
| Dec. 1 AM | Launch | Publish primary story and ask; activate email, web, social, phone, and ambassadors. | _____ |
| Dec. 1 midday | Progress | Report authentic progress, thank early donors, and respond quickly to questions or issues. | _____ |
| Dec. 1 PM | Final reminder | Use urgency tied to impact and deadline; keep gratitude prominent. | _____ |
| Dec. 2-4 | 48-hour follow-up | Thank every donor promptly; report outcome; resolve failed gifts; flag personal follow-up. | _____ |

## Giving Tuesday Go/No-Go Test

| Ready | Required confirmation |
| --- | --- |
| ☐ | All links and forms tested on desktop and mobile |
| ☐ | Automated receipts and internal alerts verified |
| ☐ | Phone, email, social, and web messages aligned |
| ☐ | Match language and restrictions confirmed |
| ☐ | Gift processing and donor-service coverage assigned |
| ☐ | Thank-you message and outcome update ready |

DECEMBER DONOR COMMUNICATION CALENDAR

# Coordinate the Final Month Without Overwhelming Donors

December objective: create a connected sequence of impact, appreciation, urgency, and personal follow-up.

| Date | Purpose | Message goal | Donor action | Owner |
| --- | --- | --- | --- | --- |
| Tue., Dec. 1 | Giving Tuesday | Primary campaign message and coordinated multichannel outreach. | Give / share | _____ |
| Wed.-Fri., Dec. 2-4 | Immediate gratitude | Prompt receipt, thank-you, results update, and failed-gift follow-up. | Feel appreciated | _____ |
| Mon.-Fri., Dec. 7-11 | Impact proof | Share a story, outcome, testimonial, or progress update. | Understand impact | _____ |
| Mon.-Fri., Dec. 14-18 | Year-end opportunity | Connect the remaining need to a specific donor-funded result. | Give by Dec. 31 | _____ |
| Mon.-Wed., Dec. 21-23 | Personal outreach | Call priority donors, open proposals, lapsed donors, and incomplete pledges. | Talk / decide | _____ |
| Thu.-Fri., Dec. 24-25 | Holiday pause | Use only mission-appropriate gratitude or previously planned seasonal messages. | Feel connected | _____ |
| Mon., Dec. 28 | Final-week launch | State progress, remaining opportunity, deadline, and giving options. | Give | _____ |
| Wed., Dec. 30 | 48-hour reminder | Use a short message with one story, one need, and one action. | Give | _____ |
| Thu., Dec. 31 AM | Final day | Remind donors of the deadline and provide direct assistance if needed. | Give today | _____ |
| Thu., Dec. 31 PM | Final hours | Send only to appropriate, engaged segments; keep the message concise. | Give now | _____ |

Cadence rule Segment before increasing frequency. Suppress donors after they give when appropriate, and replace additional asks with prompt appreciation.

## Channel Coordination Check

| Channel | Final coordination entry |
| --- | --- |
| Direct mail | Drop date: ________ ¦ In-home target: ________ ¦ Reply code: ________ |
| Email | Segments: ____________________ ¦ Suppression rule: ____________________ |
| Telephone | Priority groups: ______________ ¦ Call window: _______________________ |
| Text | Consent-confirmed audience: ______ ¦ Send dates: ________________________ |
| Website/social | Landing page owner: __________ ¦ Posting calendar: _________________ |

YEAR-END APPRECIATION CHECKLIST

# Make Every Gift the Beginning of the Next Relationship

Appreciation should be prompt, personal, specific, accurate, and matched to the donor's significance and preferences.

| Done | Timing | Appreciation action | Owner |
| --- | --- | --- | --- |
| ☐ | Within minutes/hours | Send an accurate receipt or acknowledgment confirming the gift. | _____ |
| ☐ | Within 24-48 hours | Thank priority, major, new, upgraded, monthly, and long-term donors personally. | _____ |
| ☐ | Within 3 business days | Resolve failed gifts, duplicate gifts, address questions, and correct records. | _____ |
| ☐ | Within 5 business days | Send a warm acknowledgment letter or email appropriate to the donor and gift. | _____ |
| ☐ | Within 1-2 weeks | Report campaign progress or results and connect generosity to impact. | _____ |
| ☐ | By Jan. 15 | Complete promised follow-up, tribute notices, pledge reminders, and fulfillment. | _____ |
| ☐ | By Jan. 29 | Welcome new donors and invite them to take a next relational step. | _____ |

## Priority Donor Groups

| Group | Appreciation emphasis |
| --- | --- |
| New donors | Welcome them; explain what happens next; ask about interests and preferences. |
| Monthly donors | Recognize continuing commitment and cumulative impact. |
| Upgraded donors | Acknowledge the increased confidence represented by the larger gift. |
| Major donors | Use executive, board, or relationship-manager outreach appropriate to the relationship. |
| Lapsed/reactivated donors | Welcome them back without emphasizing the lapse or creating guilt. |
| Tribute donors | Confirm recognition and complete any notification promised. |
| Non-donors who engaged | Thank them for attention, advocacy, volunteering, or sharing; keep the door open. |

A useful thank-you answers three questions Did you notice me? Did my gift matter? Do I understand what happens next?

POST-CAMPAIGN FOLLOW-UP SCHEDULE

# Close the Loop and Carry Momentum Forward

January objective: reconcile results, complete donor care, learn from performance, and convert campaign participation into lasting relationships.

| Timing | Focus | Action | Lead | Done |
| --- | --- | --- | --- | --- |
| Jan. 4-8 | Reconcile | Reconcile gifts, deposits, designations, pledges, soft credits, match totals, and expenses. | Finance / Development | _____ |
| Jan. 4-8 | Donor care | Complete receipts, acknowledgments, failed-gift outreach, and urgent questions. | Donor Services | _____ |
| Jan. 11-15 | Fulfill | Complete tribute notices, premiums, reports, call-backs, and campaign promises. | Development | _____ |
| Jan. 11-15 | Report | Share preliminary results and gratitude with staff, board, volunteers, and donors. | Leadership | _____ |
| Jan. 18-22 | Analyze | Review results by audience, channel, message, timing, gift level, and donor status. | Development | _____ |
| Jan. 18-22 | Retain | Launch new-donor welcome and monthly-giving/next-step paths where appropriate. | Development | _____ |
| Jan. 25-29 | Debrief | Document decisions, lessons, fixes, and recommendations for the next campaign. | Campaign Team | _____ |
| Jan. 25-29 | Steward | Schedule first-quarter impact updates, calls, visits, and board touchpoints. | Development | _____ |

## Campaign Results Dashboard

| Measure | 2026 result | Context / next action |
| --- | --- | --- |
| Gross revenue | $____________ | Goal: $____________ |
| Campaign expense | $____________ | Budget: $__________ |
| Net revenue | $____________ | Prior year: $_______ |
| Donors / response rate | ________ / ________% | Prior year: ________% |
| Average gift | $____________ | Prior year: $_______ |
| New donors | ______________ | 90-day retention plan: Yes / No |
| Reactivated donors | ______________ | Personal follow-up: Yes / No |
| Monthly donors added/upgraded | ________ / ________ | Annualized value: $_______ |

EXECUTIVE CLOSEOUT

# Campaign Debrief & Next-Step Decisions

Complete this page with the campaign team and share the key conclusions with executive leadership and the board.

| Leadership question | Decision / evidence |
| --- | --- |
| What worked best? | ____________________________________________________________ ____________________________________________________________ |
| What underperformed? | ____________________________________________________________ ____________________________________________________________ |
| What did donors tell us? | ____________________________________________________________ ____________________________________________________________ |
| What should we stop? | ____________________________________________________________ ____________________________________________________________ |
| What should we repeat or expand? | ____________________________________________________________ ____________________________________________________________ |
| What must be fixed before the next campaign? | ____________________________________________________________ ____________________________________________________________ |

## 90-Day Relationship Commitments

| # | Commitment | Owner | Due |
| --- | --- | --- | --- |
| 1 | ____________________________________________ | ________ | ________ |
| 2 | ____________________________________________ | ________ | ________ |
| 3 | ____________________________________________ | ________ | ________ |
| 4 | ____________________________________________ | ________ | ________ |

Keep the conversation going If your goal is improving donor retention, preparing for Giving Tuesday, or building momentum before year-end, Donor Outreach by JMA can help turn conversations into lasting commitments.

DONOR OUTREACH BY JMA

Telephone fundraising • Stewardship calling • LYBUNT/SYBUNT reactivation • Major donor qualification • Data enhancement • Campaign strategy

720 3 Mile Rd NW, Ste 2, Grand Rapids, MI 49544  |  (616) 453-8711